## roles for non smu owned (2)
Capital Projects Roles and Responsibilities
Roles for Non SMU Owned Houses
Exhibit C
December 8, 2008
Group/Individual | Role/Responsibiltiy | Meeting Frequency
CPCC | Oversee and coordinate all captial activities | Monthly
Oversight Committee | Determine whether campus standards are to be applied to project | As required
Approve schematic design
Review to ensure adequate project management is assigned to the project
Approve use of any University-provided services (e.g., wireless connectivity)
Owner | Define program needs of the project | As needed but at least monthly
Official communication channel between architect, contractor, Oversight Committee and CPPO on all issues related to the project
Manage the project, resolving all technical issues
Establish sub-committees as necessary for specific portions of the project
CPPO/Project Manager | Review architectural specifications and construction plans to ensure they are consistent with the type and quality of construction on campus | As needed
Review project budget
Review pay applications to protect the University's interests, ensuring that work performed to date supports the amounts advanced.
Communicate with owner and or program expert on issues involving program
Review documents relating to the project, including change orders, to protect the University's interests in the type and quality of the building as well as the amounts advanced related to any loan agreements
Receive copy of Substantial Completion certificate, Certificate of Occupancy, copy of O&M manuals, copy of As-Built drawings and punch list sign off prior to release of final draw on loan
VPSA | Chair of the Oversight Committee | As needed
Advise President on various issues related to the project

## non-smu owned houses
Capital Projects Process
For Non-SMU-owned Fraternity/Sorority Houses
Exhibit D
December 8, 2008
CPPO
Oversight
Group
Owner
Architect
Contractor
Owner's Project Manager, if used

## roles for smu owned
Capital Projects Roles and Responsibilities
Roles for University Owned Houses
Exhibit A
December 8, 2008
Group/Individual | Role/Responsibility | Meeting Frequency
CPCC | Oversee and coordinate all capital activities | Monthly
Oversight Committee | Approve architect selection | Quarterly or as otherwise called by the Committee
Approve schematic design
Approve contractor selection
Resolve scope, budget and similar issues that arise during project
Determine if sustainable design certification is appropriate/desired
Determine whether campus standards are to be applied to project
Determine whether project will placed on the central plant system for utilities
User Group | Define program of the project | as needed but at least monthly
Advise CPPO on the program needs of the project and then CPPO will coordinate the development of the formal program with the design team
Establish sub-committees as necessary for specific portions of the project
CPPO/Project Manager | Official communication channel between architect, contractor, end users and end users' owner's representatives on all issues related to the project | as needed
Resolve all technical issues related to the project with input from the user group on programmatic issues
Communicate with user group and or program expert on issues involving program
Manage and oversee schedule and budget
Review all documents relating to the project
VPSA | Review all documents related to project | as needed
Chair of the Oversight Committee
Advise President on various issues related to the project

## smu owned houses
Capital Projects Process
For SMU-owned Fraternity/Sorority Houses
Exhibit B
December 8, 2008
Benefits to this Process:
1. Provides clear communication internally among SMU entities and between SMU and the architects
and contractor
2. Ensures most efficient use of resources and avoids time delays due to communications confusion
3. Ensures the most effective negotiating is occurring and that the best prices are being realized
4. Puts those with the expertise in direct contact with the architect and contractor and allows the user group
to provide and receive input through CPPO to/from the necessary external parties
Notes: | It is understood that the CPCC is the guiding committee for all capital projects on campus.
User group includes fraternity/sorority representation.
Oversight Group
User Group
CPPO
(Associate Vice President, Director, Planning, Design and Construction, Project Manager)
Architect
Contractor